## Report
Daily Report
Reporting period |  |  | From |  | 2022-10-31 |  |  | To | 2022-11-04 | [8 empty] | Report date |  | 2022-11-04 | Writer |  | Si Thu Lwi n
`
Date | Project ID |  | WBS No |  |  | Task | [6 empty] | Deliverables / Document | Begin Date | End Date | Progress | Hour | Delay/ Forward | Reason |  |  | Approval1 |  | Approval2 | Approval3
[6 empty] | Function ID |  |  | Category |  | Activities | Description
2022-10-31 | BBMS-PT |  | PT_WBS_1.0 |  |  | 2.5.4 |  |  | Detail Design |  | Creation | Screen Transition |  | 2022-10-31 | 2022-10-31 | 50% | 3 |  |  |  |  | Kyaw Swar Thein
Mon | BBMS-PT |  | PT_WBS_1.0 |  |  | 2.5.4 |  |  | Detail Design |  | Creation | Screen Transition |  | 2022-10-31 | 2022-10-31 | 50% | 3
2022-11-01 | BBMS-PT |  | PT_WBS_1.0 |  |  | 2.5.4 |  |  | Detail Design |  | Creation | Screen Transition |  | 2022-10-25 | 2022-10-25 | 50% | 3 |  |  |  |  | Kyaw Swar Thein
Tue | BBMS-PT |  | PT_WBS_1.0 |  |  | 2.5.4 |  |  | Detail Design |  | Supporting | Screen Transition |  | 2022-10-25 | 2022-10-25 | 50% | 3
2022-11-02 | BBMS-PT |  | PT_WBS_1.0 |  |  | 2.5.4 |  |  | Detail Design |  | Supporting | Screen Transition |  | 2022-10-26 | 2022-10-26 | 50% | 3 |  |  |  |  | Kyaw Swar Thein
Wed
| BBMS-PT |  | PT_WBS_1.0 |  |  | 2.5.4 |  |  | Detail Design |  | Supporting | Screen Transition |  | 2022-10-26 | 2022-10-26 | 50% | 3
2022-11-03 | BBMS-PT |  | PT_WBS_1.0 |  |  | 2.5.4 |  |  | Detail Design |  | Creation | Screen Transition |  | 2022-10-27 | 2022-10-27 | 50% | 3 |  |  |  |  | Kyaw Swar Thein
Thu | BBMS-PT |  | PT_WBS_1.0 |  |  | 2.5.4 |  |  | Detail Design |  | Review | Screen Transition |  | 2022-10-27 | 2022-10-27 | 50% | 3
2022-11-04 | BBMS-PT |  | PT_WBS_1.0 |  |  | 2.5.4 |  |  | Detail Design |  | Modification | Screen Transition |  | 2022-10-28 | 2022-10-28 | 50% | 3 |  |  |  |  | Kyaw Swar Thein
Fri
[6 empty] | 2.5.4 |  |  | Detail Design |  | Creation | Screen Transition |  | 2022-10-28 | 2022-10-28 | 50% | 3
Next Week Schedule
Project ID |  | WBS No. |  | Task | [9 empty] | Begin Date | End Date | Remarks
BBMS-PT |  | PT_WBS_1.0 |  | Detail Design 2.1 Design Spec | [9 empty] | 2022-10-29 | 2022-10-29
BBMS-PT |  | PT_WBS_1.0 |  | Team Review and Revision of 01. Basic Design files | [9 empty] | 2022-10-30 | 2022-10-30
Issues
Project ID |  | WBS No. |  | Date |  |  | Name |  |  | Remark

## Report (sample)
Daily Report
Reporting period |  |  | From |  | 2012-03-15 |  |  | To | 2012-03-21 | [8 empty] | Report date |  | 2012-03-27 | Writer
`
Date | Project ID |  | WBS No |  |  | Task | [6 empty] | Deliverables / Document | Begin Date | End Date | Progress | Hour | Delay/ Forward | Reason |  |  | Approval1 | Approval2 | Approval3
[6 empty] | Function ID |  |  | Category |  | Activities | Description
2012-03-15 | MEDI |  | - |  |  | - |  |  | Project Management |  | - | Team Meeting |  |  |  |  | 0.5
2012-03-15
| MEDI |  | - |  |  | - |  |  | Project Management |  | - | Daily Report Creation | Zin May Thu - 20120315-0321.xls |  |  | 100% | 0.25
| MEDI |  | - |  |  | - |  |  | Project Management |  | - | Meeting Minutes Creation(Daily) | (MedI)MeetingMinutes_March.xls |  |  | 100% | 0.25
| MEDI |  | - |  |  | - |  |  | Project Management |  | - | Teleconference Meeting |  |  |  |  | 0.5
| MEDI |  | - |  |  | - |  |  | Project Management |  | - | Meeting Minutes Creation(Tele) | MeetingMinutes_20120315_MediaInventory.doc |  |  | 100% | 0.25
| MEDI |  | - |  |  | - |  |  | Project Management |  | - | Meeting Minutes Confirmation(Tele) |  |  |  |  | 0.25
| MEDI |  | - |  |  | - |  |  | Integrated Test Specification |  | Q&A | Q&A Related ITb | [MEDI]QA_000177.xls |  |  | 100% | 0.25
| MEDI |  | - |  |  | - |  |  | Project Management |  | - | EMail Handling | [MEDI]QA_000177.xls |  |  |  | 0.25
| MEDI |  | MD 11.4.2.6 |  |  | MST0301 |  |  | Basic Design |  | Translation | Program Development Checking(QC) | (MedI)_MST0301-QCLeaderCheckList_MasterTableManagementChangeInput.xls | 2012-03-15 | 2012-03-19 | 100% | 2.5
| MEDI |  | MD 11.4.2.6 |  |  | MST0303 |  |  | Coding Development |  | Review | Program Development Checking(QC) | (MedI)_MST0303-QCLeaderCheckList_MasterTableManagementChangeResult.xls | 2012-03-15 | 2012-03-19 | 100% | 2
2012-03-16 | - |  | - |  |  | - |  |  | Project Management |  | - | Team Meeting |  |  |  |  | 0.5
2012-03-16
| - |  | - |  |  | - |  |  | Project Management |  | - | Daily Report Creation | Zin May Thu - 20120315-0321.xls |  |  | 100% | 0.25
| - |  | - |  |  | - |  |  | Project Management |  | - | Meeting Minutes Creation(Daily) | (MedI)MeetingMinutes_March.xls |  |  | 100% | 0.25
| MEDI |  | MD 11.4.2.6 |  |  | MST0302 |  |  | Coding Development |  | Review | Program Development Checking(QC) | (MedI)_MST0302-QCLeaderCheckList_MasterTableManagementChangeConfirmation.xls | 2012-03-15 | 2012-03-19 | 100% | 3.5
| MEDI |  | MD 11.4.2.6 |  |  | MST0402 |  |  | Coding Development |  | Review | Program Development Checking(QC) | (MedI)_MST0402-QCLeaderCheckList_MasterTableManagementDeletionResult.xls | 2012-03-15 | 2012-03-19 | 100% | 1
| ORCA |  | MD 1.5.3.6 |  |  | STK0101 |  |  | Unit Test Specification |  | Review | Unit Test Specification Checking(QC) | (MedI)_UnitTestSpec_STK0101_ver2.0.xls | 2012-03-16 | 2012-03-20 | 100% | 1.5
2012-03-17
2012-03-17
2012-03-18
2012-03-18
2012-03-19 | - |  | - |  |  | - |  |  | Project Management |  | - | Team Meeting |  |  |  |  | 0.5
2012-03-19
| - |  | - |  |  | - |  |  | Project Management |  | - | Daily Report Creation | Zin May Thu - 20120315-0321.xls |  |  | 100% | 0.25
| - |  | - |  |  | - |  |  | Project Management |  | - | Meeting Minutes Creation(Daily) | (MedI)MeetingMinutes_March.xls |  |  | 100% | 0.25
| - |  | - |  |  | - |  |  | ACE Internal Work |  | - | Meeting(ODC All QC Leader) |  |  |  |  | 1
| - |  | - |  |  | - |  |  | ACE Internal Work |  | - | Meeting Minutes Creation(ODC All QC Leader) | [ODC] QC Leader Weekly Meeting Agenda (15).doc, [ODC] QC Leader Weekly Meeting Minute (14).doc |  |  | 100% | 0.5
| - |  | - |  |  | - |  |  | Improvement Training |  | - | Training(Japanese) |  |  |  |  | 1
| MEDI |  | MD 11.4.2.6 |  |  | MST0201 |  |  | Coding Development |  | Review | Program Development Checking(QC) | (MedI)_MST0201-QCLeaderCheckList_MasterTableManagementReferInput.xls | 2012-03-15 | 2012-03-19 | 100% | 1
| ORCA |  | MD 1.5.3.6 |  |  | STK0102 |  |  | Unit Test Specification |  | Review | Unit Test Specification Checking(QC) | (MedI)_UnitTestSpec_STK0102_ver2.0.xls | 2012-03-16 | 2012-03-20 | 100% | 1.25
| ORCA |  | MD 1.5.3.6 |  |  | STK0103 |  |  | Unit Test Specification |  | Review | Unit Test Specification Checking(QC) | (MedI)_UnitTestSpec_STK0103_ver2.0.xls | 2012-03-16 | 2012-03-20 | 100% | 1.25
2012-03-20 | ORCA |  | - |  |  | - |  |  | Project Management |  | - | Team Meeting |  |  |  |  | 0.5
2012-03-20
| ORCA |  | - |  |  | - |  |  | Project Management |  | - | Daily Report Creation | Zin May Thu - 20120315-0321.xls |  |  | 100% | 0.25
| ORCA |  | - |  |  | - |  |  | Project Management |  | - | Meeting Minutes Creation(Daily) | (MedI)MeetingMinutes_March.xls |  |  | 100% | 0.25
| - |  | - |  |  | - |  |  | ACE Internal Work |  | - | Meeting(ACE All Staff) |  |  |  |  | 1.5
| ORCA |  | MD 1.5.3.6 |  |  | STK0201 |  |  | Unit Test Specification |  | Review | Unit Test Specification Checking(QC) | (MedI)_UnitTestSpec_STK0201_ver2.0.xls | 2012-03-16 | 2012-03-20 | 100% | 1.5
| ORCA |  | MD 1.5.3.6 |  |  | STK0202 |  |  | Unit Test Specification |  | Review | Unit Test Specification Checking(QC) | (MedI)_UnitTestSpec_STK0202_ver2.0.xls | 2012-03-16 | 2012-03-20 | 100% | 1
| ORCA |  | MD 1.5.3.7 |  |  | - |  |  | Unit Test Execution |  | Review | Project Testing | (MedI)_UnitTestSpec_STK0102_ver2.0.xls | 2012-03-20 | 2012-03-21 | 100% | 1
| ORCA |  | - |  |  | - |  |  | Project Management |  | - | Template Creation | (Project ID)_ITb_ver{Version No}.xls |  |  | 80% | 1
2012-03-21 | - |  | - |  |  | - |  |  | Project Management |  | - | Team Meeting |  |  |  |  | 0.5
2012-03-21
| - |  | - |  |  | - |  |  | Project Management |  | - | Daily Report Creation | Zin May Thu - 20120315-0321.xls |  |  | 100% | 0.25
| - |  | - |  |  | - |  |  | Project Management |  | - | Meeting Minutes Creation(Daily) | (MedI)MeetingMinutes_March.xls |  |  | 100% | 0.25
| - |  | - |  |  | - |  |  | Improvement Training |  | - | Training(Japanese) |  |  |  |  | 1
| ORCA |  | - |  |  | - |  |  | Project Management |  | - | Template Creation | (Project ID)_ITb_ver{Version No}.xls |  |  | 100% | 1
| MEDI |  | - |  |  | - |  |  | System Test Specification |  | Translation | System Test Specification Translation | [ORCA]ST Spec and Result ver1.01.xls |  |  | 100% | 1
| MEDI |  | - |  |  | - |  |  | Performance Test Specification |  | Discussion | Performance Test Discussion |  |  |  |  | 1
| ORCA |  | - |  |  | - |  |  | Coding Development |  | R&D | Development Research(usin rich faces) |  |  |  | 100% | 1
| MEDI |  | - |  |  | - |  |  | Integrated Test Specification |  | Preparation | ITb Specification Preparation |  |  |  | 100% | 1
Next Week Schedule
Project ID |  | WBS No. |  | Task | [9 empty] | Begin Date | End Date | Remarks
MEDI |  | MD 11.4.3.5.3 |  | MST0301-Master Table Management Change Input (Unit Test Evidence Checking(QC)) | [9 empty] | 2012-03-23 | 2012-03-23
MEDI |  | MD 11.4.3.4.4 |  | MST0302-Master Table Management Change Confirmation (Unit Test Evidence Checking(SE-L)) | [9 empty] | 2012-03-23 | 2012-03-23
MEDI |  | MD 11.4.3.5.4 |  | MST0302-Master Table Management Change Confirmation (Unit Test Evidence Checking(QC)) | [9 empty] | 2012-03-26 | 2012-03-26
Issues
Project ID |  | WBS No. |  | Date |  |  | Name |  |  | Remark
Formulas:
Date = [Date, row above]

## (Rules)
Report Glossary
From |  | Report Start Date
To |  | Report End Date
Report Date |  | Report Send Date
Writer |  | Name Of The Writer
Project ID |  | Project ID of the assignment
If there is no exact project ID, fill "-". This cost will be shared by all functions
WBS No. |  | WBS No.
Function ID |  | Function ID of the assignment
If there is no exact function ID, fill "-". This cost will be shared by all functions
Category |  | Category of the assignment
Refer to Task Type Explanation sheet.
Activities |  | Activities of the assignment
Refer to Task Type Explanation sheet.
Description |  | Detail description of the assignment
Refer to Description title of Data sheet.
Deliverable Document |  | Output documents of the assignment
Begin Date/End Date |  | Assignment's start date and end date from WBS
Progress |  | Complete percentage of the assignment
|  |  | Progress |  |  | Definition of Progress Rate
|  |  | 0% |  |  | not starting
|  |  | 20% |  |  | working state (less than half)
|  |  | 40% |  |  | working state (half)
|  |  | 60% |  |  | working state (more than half)
|  |  | 80% |  |  | finishing
|  |  | 100% |  |  | finishing self check
Hour |  | Time taken of the assignment by hour
Delay/Forward |  | Delay or Forward man month of the assignment.
Example
[5 empty] | Delay |  | -1MD | -2.5MD
[5 empty] | Forward |  | +1MD | +2.5MD
Note
Need to enter only 1 or -1 at first cell
Fill only when progress reach 100%
Fill the issue
Reason |  | Reason of the delay or forward
Approval 1 |  | Replace 1 with Leader Name
Approval 2 |  | Replace 2 with PM Name
Additional Rules
1 | Total hour per day(exclude other activities) is | [5 empty] | 7
2 | Every records must have category and activities
3 | There must be space line between every records.(For report reader utilities)
4 | Must be fill only one line in Deliverable Document. (For report reader utilities)

## (Data)
Category | Activities | Explanation For Activities
Project Management | Creation
Requirement Definition | Review
Basic Design | Modification
Detail Design | Supporting
Coding Development | Discussion
Spec Development | Translation
Unit Test Specification | Preparation | => also including studying time
Unit Test Execution | Q&A
Integrated Test Specification | R&D
Integrated Test Execution | Other | => Client side training, incident recovery and any other operation on production environment.
Integrated Test Evidence | Investigation
System Test Specification | Customer Support
System Test Execution | -
System Test Evidence
Performance Test Specification
Performance Test Execution
Performance Test Evidence
User Acceptance Test Specification
User Acceptance Test Execution
User Training
Operation and Maintenance
Environmental Tuning
DAT Internal Work
Training For Project
Improvement Training
Idling Work For Project
Idling Work
Leave
Service Level Maintainence
Incident Management
Unit Test Evidence
DAT All Staff Meeting
Description
Project Management |  | Basic Design | Detail Design | Unit Test Specification | System Test Specification | Preparation
Daily Report Creation |  | Basic Design Designing | Detail Design Discussion | Unit Test Discussion | System Test Discussion | Documents Preparation
Daily Report Checking |  | Basic Design Studying | Q&A Related Detail Design | Q&A Related Unit Test | Q&A Related System Test | Preparation For Training
Weekly Report Creation |  | Basic Design Discussion | Business Application Preparation | Test Data Preparation | System Test Specification Preparation | Basic Design Preparation
Evaluation Report Creation |  | HTML Mock Preparation | Business Application Translation | Unit Test Specification Preparation | System Test Specification Translation | Detail Design Preparation
Meeting Minutes Creation(Daily) |  | HTML Mock Translation | Business Application Creation | Unit Test Specification Translation | System Test Specification Creation | Program Development Preperation
Meeting Minutes Creation(Tele) |  | HTML Mock Creation | Business Application Modification(DIR-BI Reviews) | Unit Test Specification Creation | System Test Specification Modification(DIR-BI Reviews) | Coverage Report Preperation
Meeting Minutes Confirmation(Tele) |  | HTML Mock Modification(DIR-BI Reviews) | Business Application Modification(SE-L Reviews) | Unit Test Specification Modification(DIR-BI Reviews) | System Test Specification Modification(SE-L Reviews) | Unit Test Preperation
Agenda Creation(Tele) |  | HTML Mock Modification(SE-L Reviews) | Business Application Modification(QC Reviews) | Unit Test Specification Modification(SE-L Reviews) | System Test Specification Modification(QC Reviews) | Integrated Test Preperation
Agenda Confirmation(Tele) |  | HTML Mock Modification(QC Reviews) | Business Application Supporting | Unit Test Specification Modification(QC Reviews) | System Test Specification Supporting | Deliverable Preparation
Teleconference Meeting |  | HTML Mock Supporting | Business Application Checking(SE-L) | Unit Test Specification Supporting | System Test Specification Checking(SE-L)
Team Meeting |  | HTML Mock Checking(SE-L) | Business Application Checking(QC) | Unit Test Specification Checking(SE-L) | System Test Specification Checking(QC) | Discussion
WBS Creation |  | HTML Mock Checking(QC) | Business Application Rechecking(SE-L) | Unit Test Specification Checking(QC) | System Test Specification Rechecking(SE-L) | Basic Design Discussion
WBS Modification |  | HTML Mock Rechecking(SE-L) | Business Application Rechecking(QC) | Unit Test Specification Rechecking(SE-L) | System Test Specification Rechecking(QC) | Detail Design Discussion
Studying(xxxxxx) |  | HTML Mock Rechecking(QC) | Service Specification Preparation | Unit Test Specification Rechecking(QC) |  | Program Development Discussion
Rule & Standard Creation |  | Q&A Related HTML Mock | Service Specification Translation | Project Testing | System Test Execution | Coverage Report Discussion
Rule & Standard Modification |  | Screen Design Preparation | Service Specification Creation |  | System Test Execution Preparation | Unit Test Discussion
Rule & Standard Confirmation |  | Screen Design Translation | Service Specification Modification(DIR-BI Reviews) | Unit Test Execution | System Test Execution | Integrated Test Discussion
Template Creation |  | Screen Design Creation | Service Specification Modification(SE-L Reviews) | Unit Test Execution Preparation | System Test Execution Re-Execution(DIR-BI Reviews) | Deliverable List Discussion
Template Modification |  | Screen Design Modification(DIR-BI Reviews) | Service Specification Modification(QC Reviews) | Unit Test Execution | System Test Execution Re-Execution(SE-L Reviews) | Rule & Standard Discussion
Template Confirmation |  | Screen Design Modification(SE-L Reviews) | Service Specification Supporting | Unit Test Execution Re-Execution(DIR-BI Reviews) | System Test Execution Re-Execution(QC Reviews) | Template Discussion
Directory Structure Management |  | Screen Design Modification(QC Reviews) | Service Specification Checking(SE-L) | Unit Test Execution Re-Execution(SE-L Reviews) | System Test Execution Supporting | Requirement Definition Discussion
Project Progress Report Creation |  | Screen Design Supporting | Service Specification Checking(QC) | Unit Test Execution Re-Execution(QC Reviews) | System Test Execution Checking(SE-L)
Q&A Handling |  | Screen Design Checking(SE-L) | Service Specification Rechecking(SE-L) | Unit Test Execution Supporting | System Test Execution Checking(QC)
Screen List Creation |  | Screen Design Checking(QC) | Service Specification Rechecking(QC) | Unit Test Execution Checking(SE-L) | System Test Execution Rechecking(SE-L)
EMail Handling |  | Screen Design Rechecking(SE-L) | DAO Specification Preparation | Unit Test Execution Checking(QC) | System Test Execution Rechecking(QC)
Translation For xxxxxxxxxxxxxxxxxx |  | Screen Design Rechecking(QC) | DAO Specification Translation | Unit Test Execution Rechecking(SE-L)
Deliverable List Creation |  | Q&A Related Screen Design | DAO Specification Creation | Unit Test Execution Rechecking(QC) | System Test Evidence
Delivery(xxxxx) |  | Physical ERD Preparation | DAO Specification Modification(DIR-BI Reviews) |  | System Test Evidence Preparation
|  | Physical ERD Translation | DAO Specification Modification(SE-L Reviews) | Unit Test Evidence | System Test Evidence Taking
PM Risk & Issue Handling |  | Physical ERD Creation | DAO Specification Modification(QC Reviews) | Unit Test Evidence Preparation | System Test Evidence Re-Taking(DIR-BI Reviews)
|  | Physical ERD Modification(DIR-BI Reviews) | DAO Specification Supporting | Unit Test Evidence Taking | System Test Evidence Re-Taking(SE-L Reviews)
|  | Physical ERD Modification(SE-L Reviews) | DAO Specification Checking(SE-L) | Unit Test Evidence Re-Taking(DIR-BI Reviews) | System Test Evidence Re-Taking(QC Reviews)
|  | Physical ERD Modification(QC Reviews) | DAO Specification Checking(QC) | Unit Test Evidence Re-Taking(SE-L Reviews) | System Test Evidence Supporting
Training For Project |  | Physical ERD Supporting | DAO Specification Rechecking(SE-L) | Unit Test Evidence Re-Taking(QC Reviews) | System Test Evidence Checking(SE-L)
DIR-BI Business Trip |  | Physical ERD Checking(SE-L) | DAO Specification Rechecking(QC) | Unit Test Evidence Supporting | System Test Evidence Checking(QC)
Training(xxxxxxxx) |  | Physical ERD Checking(QC) | DAO List Preparation | Unit Test Evidence Checking(SE-L) | System Test Evidence Rechecking(SE-L)
|  | Physical ERD Rechecking(SE-L) | DAO List Translation | Unit Test Evidence Checking(QC) | System Test Evidence Rechecking(QC)
Environmental Tuning |  | Physical ERD Rechecking(QC) | DAO List Creation | Unit Test Evidence Rechecking(SE-L) | System Test Delivery Checking
Hardware Failure |  | Q&A Related Physical ERD | DAO List Modification(DIR-BI Reviews) | Unit Test Evidence Rechecking(QC)
Server Preparation |  | Data Flow Diagram Preparation | DAO List Modification(SE-L Reviews) | Unit Test Delivery Checking | Performance Test Specification
Server Backup Management |  | Data Flow Diagram Translation | DAO List Modification(QC Reviews) |  | Performance Test Discussion
Installation(xxxxx) |  | Data Flow Diagram Creation | DAO List Supporting | ITa Specification | Q&A Related Performance Test
|  | Data Flow Diagram Modification(DIR-BI Reviews) | DAO List Checking(SE-L) | Integrated Test Discussion | Performance Test Specification Preparation
Improvement Training |  | Data Flow Diagram Modification(SE-L Reviews) | DAO List Rechecking(SE-L) | Q&A Related Integrated Test | Performance Test Specification Translation
Training(xxxxxxxx) |  | Data Flow Diagram Modification(QC Reviews) | DAO List Checking(QC) | Coverage Report Creation | Performance Test Specification Creation
Training(Japanese) |  | Data Flow Diagram Supporting | DAO List Rechecking(QC) | ITa Specification Preparation | Performance Test Specification Modification(DIR-BI Reviews)
Training(English) |  | Data Flow Diagram Checking(SE-L) | Service List Preparation | ITa Specification Translation | Performance Test Specification Modification(SE-L Reviews)
Training(Management) |  | Data Flow Diagram Checking(QC) | Service List Translation | ITa Matrix Creation | Performance Test Specification Modification(QC Reviews)
|  | Data Flow Diagram Rechecking(SE-L) | Service List Creation | ITa Specification Creation | Performance Test Specification Supporting
Leave |  | Data Flow Diagram Rechecking(QC) | Service List Modification(DIR-BI Reviews) | ITa Specification Modification(DIR-BI Reviews) | Performance Test Specification Checking(SE-L)
Leave |  | Q&A Related Data Flow Diagram | Service List Modification(SE-L Reviews) | ITa Specification Modification(SE-L Reviews) | Performance Test Specification Checking(QC)
Half Day Leave |  | Class Diagram Preparation | Service List Modification(QC Reviews) | ITa Specification Modification(QC Reviews) | Performance Test Specification Rechecking(SE-L)
|  | Class Diagram Translation | Service List Supporting | ITa Specification Supporting | Performance Test Specification Rechecking(QC)
ACE Internal Work |  | Class Diagram Creation | Service List Checking(SE-L) | ITa Specification Checking(SE-L)
Electricity Problem |  | Class Diagram Modification(DIR-BI Reviews) | Service List Rechecking(SE-L) | ITa Specification Checking(QC) | Performance Test Execution
Meeting(ODC All Project Manager) |  | Class Diagram Modification(SE-L Reviews) | Service List Checking(QC) | ITa Specification Rechecking(SE-L) | Performance Test Execution Preparation
Meeting(ODC All SE Leader) |  | Class Diagram Modification(QC Reviews) | Service List Rechecking(QC) | ITa Specification Rechecking(QC) | Performance Test Execution
Meeting(ODC All PG Leader) |  | Class Diagram Supporting | Detail Design Delivery Checking |  | Performance Test Execution Re-Execution(DIR-BI Reviews)
Meeting(ODC All QC Leader) |  | Class Diagram Checking(SE-L) |  | ITa Execution | Performance Test Execution Re-Execution(SE-L Reviews)
Meeting Minutes Creation(ODC ALL Project Manager) |  | Class Diagram Checking(QC) | Coding Development | ITa Execution Preparation | Performance Test Execution Re-Execution(QC Reviews)
Meeting Minutes Creation(ODC ALL SE Leader) |  | Class Diagram Rechecking(SE-L) | Program Development Discussion | ITa Execution | Performance Test Execution Supporting
Meeting Minutes Creation(ODC ALL PG Leader) |  | Class Diagram Rechecking(QC) | Q&A Related Coding Development | ITa Execution Re-Execution(DIR-BI Reviews) | Performance Test Execution Checking(SE-L)
Meeting Minutes Creation(ODC All QC Leader) |  | Q&A Related Class Diagram | DDL & DML Creation | ITa Execution Re-Execution(SE-L Reviews) | Performance Test Execution Checking(QC)
HR Recruitment |  | Message List Preparation | DDL & DML Modification(DIR-BI Reviews) | ITa Execution Re-Execution(QC Reviews) | Performance Test Execution Rechecking(SE-L)
Meeting(ACE All Staff) |  | Message List Translation | DDL & DML Modification(SE-L Reviews) | ITa Execution Supporting | Performance Test Execution Rechecking(QC)
Meeting(ODC All Staff) |  | Message List Ceation | DDL & DML Modification(QC Reviews) | ITa Execution Checking(SE-L)
Attending Seminar(xxxxx) |  | Message List Modification(DIR-BI Reviews) | DDL & DML Supporting | ITa Execution Checking(QC) | Performance Test Evidence
Attending Presentation(xxxxx) |  | Message List Modification(SE-L Reviews) | DDL & DML Checking | ITa Execution Rechecking(SE-L) | Performance Test Evidence Preparation
|  | Message List Modification(QC Reviews) | DDL & DML Rechecking | ITa Execution Rechecking(QC) | Performance Test Evidence Taking
|  | Message List Checking(SE-L) | Program Development |  | Performance Test Evidence Re-Taking(DIR-BI Reviews)
|  | Message List Rechecking(SE-L) | Program Modification(DIR-BI Reviews) | ITa Evidence | Performance Test Evidence Re-Taking(SE-L Reviews)
|  | Message List Checking(QC) | Program Modification(SE-L Reviews) | ITa Evidence Preparation | Performance Test Evidence Re-Taking(QC Reviews)
Text Template |  | Message List Rechecking(QC) | Program Modification(QC Reviews) | ITa Evidence Taking | Performance Test Evidence Supporting
xxxxxxxxxxxx Creation |  | Q&A Related Message List | Program Modification(Unit Test Bugs) | ITa Evidence Re-Taking(DIR-BI Reviews) | Performance Test Evidence Checking(SE-L)
xxxxxxxxxxxx Modification(DIR-BI Reviews) |  | Basic Design Delivery Checking | Program Modification(ITa Bugs) | ITa Evidence Re-Taking(SE-L Reviews) | Performance Test Evidence Checking(QC)
xxxxxxxxxxxx Modification(SE-L Reviews) |  |  | Program Modification(ITb Bugs) | ITa Evidence Re-Taking(QC Reviews) | Performance Test Evidence Rechecking(SE-L)
xxxxxxxxxxxx Modification(QC Reviews) |  | Requirement Definition | Program Modification(System Test Bugs) | ITa Evidence Supporting | Performance Test Evidence Rechecking(QC)
xxxxxxxxxxxx Modification(PG-L Reviews) |  | Requirement Definition Preparation | Program Modification(Performance Test Bugs) | ITa Evidence Checking(SE-L) | Performance Test Delivery Checking
xxxxxxxxxxxx Supporting |  | Requirement Definition Translation | Program Development Supporting | ITa Evidence Checking(QC)
xxxxxxxxxxxx Checking(SE-L) |  | Q&A Related Requirement Definition | Program Development Checking(PG-L) | ITa Evidence Rechecking(SE-L) | For Other Case
xxxxxxxxxxxx Checking(QC) |  |  | Program Development Checking(QC) | ITa Evidence Rechecking(QC) | WBS description + {Activities}
xxxxxxxxxxxx Checking(PG-L) |  | Program Design | Program Development Rechecking(PG-L) | ITa Delivery Checking
xxxxxxxxxxxx Discussion |  |  | Program Development Rechecking(QC) |  | Activities:
xxxxxxxxxxxx Preparation |  |  | Development Research(xxxxx) | ITb Specification | Creation
xxxxxxxxxxxx Translation |  | Service Level Maintenance |  | ITb Specification Preparation | Modification
|  | Production System Improvement | Spec Development | ITb Specification Translation | SE Leader Check
|  | Production System Module Update | Java Doc Creation | ITb Overall Matrix Creation | QC Leader Check
|  | Production System testing and confirmation | User Manual Creation | ITb Overall Procedure Creation | PG Leader Check
|  |  | Environment Setup Manual Creation | ITb Test Data Creation | Unit Test Execution
|  | Incident Management | Troubleshooting Manual Creation | ITb Specification(Detail Test Cases) Creation | Integrated Test Execution
|  | Incident Investigation | Installation Manual Creation | ITb Specification Modification(DIR-BI Reviews)
|  | Incident Recovery |  | ITb Specification Modification(SE-L Reviews)
ITb Specification Modification(QC Reviews)
ITb Specification Supporting
ITb Specification Checking(SE-L)
ITb Specification Checking(QC)
ITb Specification Rechecking(SE-L)
ITb Specification Rechecking(QC)
ITb Execution
ITb Execution Preparation
ITb Execution
ITb Execution Re-Execution(DIR-BI Reviews)
ITb Execution Re-Execution(SE-L Reviews)
ITb Execution Re-Execution(QC Reviews)
ITb Execution Supporting
ITb Execution Checking(SE-L)
ITb Execution Checking(QC)
ITb Execution Rechecking(SE-L)
ITb Execution Rechecking(QC)
ITb Evidence
ITb Evidence Preparation
ITb Evidence Taking
ITb Evidence Re-Taking(DIR-BI Reviews)
ITb Evidence Re-Taking(SE-L Reviews)
ITb Evidence Re-Taking(QC Reviews)
ITb Evidence Supporting
ITb Evidence Checking(SE-L)
ITb Evidence Checking(QC)
ITb Evidence Rechecking(SE-L)
ITb Evidence Rechecking(QC)
ITb Delivery Checking

## (Task Type Explanation)
Summary | Main Category | Category | Activity | Task Type
Actual Work | Project Management | Project Management | None (-) | Daily Report Creation / Checking
Weekly Report Creation
Evaluation Report Creation
Daily Meeting Minute Creation
Team Meeting / Progress Meeting / Daily Meeting
Weekly Teleconference Meeting Minute Creation / Agenda Creation
WBS Creation / Modification
Standard Documents & Templates Creation / Directory Structure Mgt
Project Progress Report Creation (Overall Status)
Handling QA
PM Risk & Issue Handling
Email Response / Reading / Writing / Forwarding / Confirmation
Spending Time for translation Japanese concerning Document and QA,conversation
|  |  | None (-) | Deliverable Preparation
|  | Training For Project | None (-) | Business Trip / Training related to project
| Task Management | Requirement Definition |  | Understanding of Requirement Definition/ Screen Development
|  | Basic Design |  | Basic Design Creation / Supporting / Checking by SE-L & QC-L / Q&A
Basic Design Mofication After DIR-BI or QC-L or SE-L Reviews
Basic Design Discussion / Preparation / Translation / Delivery Checking
|  | Detail Design | Creation,Modification,Q&A, | Detail Design Creation / Supporting / Checking by SE-L & QC-L / Q&A
|  |  | Review,Supporting,Discussion | Detail Design Mofication After DIR-BI or QC-L or SE-L Reviews
|  |  | Translation,Preparation,R&D | Detail Design Discussion / Preparation / Translation / Delivery Checking
|  | Program Design |  | Program Design Creation / Supporting / Checking by SE-L & QC-L / Q&A
Program Design Mofication After DIR-BI or QC-L or SE-L Reviews
Program Design Discussion / Preparation / Translation / Delivery Checking
|  | Coding Development |  | Coding Development / Supporting / Checking by PG-L & QC-L / Q&A
Program Design Mofication After DIR-BI or QC-L or SE-L Reviews
Program Design Discussion / Preparation / Translation / Delivery Checking
|  | Spec Development |  | User Manual/ Java Doc/ Environment Setup Manual/ Troubleshooting Manual/
Installation Manual -- Creation / Supporting / Checking
Discussion / Preparation / Translation
|  | Unit Test Specification |  | Unit Test Spec Creation / Supporting / Checking by SE-L & QC-L / Q&A
Unit Test Spec Mofication After DIR-BI or QC-L or SE-L Reviews
Unit Test Spec Discussion / Preparation / Translation / Delivery Checking
|  | Unit Test Execution | Creation,Modification,Q&A, | Unit Test Execution / Supporting / Checking by SE-L & QC-L / Q&A
|  |  | Review,Supporting,Discussion | Unit Test Re-Execution for internal/external bugs
|  |  | Translation,Preparation,R&D | Unit Test Execution Discussion / Preparation / Delivery Checking
|  | Unit Test Evidence |  | Unit Test Evidence Taking / Supporting / Checking by SE-L & QC-L / Q&A
Unit Test Evidence Re-Taking After DIR-BI or QC-L or SE-L Reviews
Unit Test Evidence Discussion / Preparation / Delivery Checking
|  | Integrated Test Specification |  | Integrated Test Spec Creation / Supporting / Checking by SE-L & QC-L / Q&A
Integrated Test Spec Mofication After DIR-BI or QC-L or SE-L Reviews
Integrated Test Spec Discussion / Preparation / Translation / Delivery Checking
|  | Integrated Test Execution | Creation,Modification,Q&A, | Integrated Test Execution / Supporting / Checking by SE-L & QC-L / Q&A
|  |  | Review,Supporting,Discussion | Integrated Test Re-Execution for internal/external bugs
|  |  | Translation,Preparation,R&D | Integrated Test Execution Discussion / Preparation / Delivery Checking
|  | Integrated Test Evidence |  | Integrated Test Evidence Taking / Supporting / Checking by SE-L & QC-L / Q&A
Integrated Test Evidence Re-Taking After DIR-BI or QC-L or SE-L Reviews
Integrated Test Evidence Discussion / Preparation / Delivery Checking
|  | System Test Specification |  | System Test Spec Creation / Supporting / Checking by SE-L & QC-L / Q&A
System Test Spec Mofication After DIR-BI or QC-L or SE-L Reviews
System Test Spec Discussion / Preparation / Translation / Delivery Checking
|  | System Test Execution | Creation,Modification,Q&A, | System Test Execution / Supporting / Checking by SE-L & QC-L / Q&A
|  |  | Review,Supporting,Discussion | System Test Re-Execution for internal/external bugs
|  |  | Translation,Preparation,R&D | System Test Execution Discussion / Preparation / Delivery Checking
|  | System Test Evidence |  | System Test Evidence Taking / Supporting / Checking by SE-L & QC-L / Q&A
System Test Evidence Re-Taking After DIR-BI or QC-L or SE-L Reviews
System Test Evidence Discussion / Preparation / Delivery Checking
|  | Performance Test Specification |  | Performance Test Spec Creation / Supporting / Checking by SE-L & QC-L / Q&A
Performance Test Spec Mofication After DIR-BI or QC-L or SE-L Reviews
Performance Test Spec Discussion / Preparation / Translation / Delivery Checking
|  | Performance Test Execution | Creation,Modification,Q&A, | Performance Test Execution / Supporting / Checking by SE-L & QC-L / Q&A
|  |  | Review,Supporting,Discussion | Performance Test Re-Execution for internal/external bugs
|  |  | Translation,Preparation,R&D | Performance Test Execution Discussion / Preparation / Delivery Checking
|  | Performance Test Evidence |  | Performance Test Evidence Taking / Supporting / Checking by SE-L & QC-L / Q&A
Performance Test Evidence Re-Taking After DIR-BI or QC-L or SE-L Reviews
Performance Test Evidence Discussion / Preparation / Delivery Checking
|  | Service Level Maintenance |  | Production systems (ongoing system) improvement
Production systems (ongoing system) module update
Production systems (ongoing system) testing and confirmation
|  | Incident Management |  | Incident Investigation
Incident Recovery and confirmation
| Others | Environmental Tuning | None (-) | Hardware Failure / Server/DB/Securities/Backup
ACE Internal Work |  | DAT Internal Work | None (-) | Electricity Problem
ODC Meeting/ Meeting Minute Creation/ ODC Related Work/ HR Recruitment
ACE All Staff Meeting/ ACE Related Work
Attending Seminar/Presentation
|  | Improvement Training | None (-) | Training(English, Japanese, Technical, Management, etc...)
|  | Half Leave | None (-) | Half Day Leave
|  | Leave | None (-) | Full Day Leave
Idling Work For Project (Waiting Time) | Idling | Idling Work For Project | None (-) | Learning Technologies(Wating For QA Answer)
Learning Technologies(Wating For Review Result)
Learning Technologies(Wating For Provided Document)
Learning Languages(Wating For QA Answer)
Learning Languages(Wating For Review Result)
Learning Languages(Wating For Provided Document)
Idling Work |  | Idling Work | None (-) | Other Activities
Self Improvement in idling time